## Kate_hours
Date | hours | task
2023-03-13 | 1.5 | Ben and Kate present/discuss eDNA cleaning workflows to Eden
2023-03-20 | 3 | discuss Eden's workflow and deliverables of contract
2023-03-29 | 5 | Ben and Kate meeting to discuss workflow and assign tasks, OBIS download + initial cleaning
2023-03-30 | 4 | GBIF setup and prepping species lists
2023-04-04 | 2 | Meet with Ben, Jenn, and Eden
2023-04-11 | 4 | Met with Ben, updated OBIS for ecoregions
2023-04-12 | 5 | Fixed loop, top 500 taxize
total | 24.5

## Ben_hours
Date | hours | task
2023-03-13 | 1.5 | Ben and Kate present/discuss eDNA cleaning workflows to Eden
2023-03-20 | 3 | discuss Eden's workflow and deliverables of contract
2023-03-29 | 2 | Ben and Kate meeting to discuss workflow and assign tasks
2023-04-04 | 2 | Meet with Kate, Jenn, and Eden
2023-04-05 | 7 | finding ecoregion/pelagic province data, pull from obis from regions
2023-04-10 | 7 | finding ecoregion/pelagic province data, pull from obis from regions
2023-04-11 | 7 | meeting with Kate, taxonomy script, research database coverage approach
2023-04-12 | 7 | checking obis inclusion with fishbase, NCBI search criteria
2023-04-13 | 5 | NCBI search criteria and fasta downloading
2023-04-14 | 3 | Python, NCBI search criteria and fasta downloading
2023-04-17 | 4 | Python, NCBI search criteria and fasta downloading
2023-04-20 | 4 | Python, BLAST seach, outut
2023-04-21 | 4 | Python, BLAST seach, outut
2023-04-24 | 5 | Python, BLAST seach, outut
61.5